# Collective Partner — Actual Process Map

First contact → live & running. The real operational process, not the marketing version. Prepared 2026-06-30. Owner: Kade.

This is what actually happens when a new founding-partner coach comes on. The website’s “How it works” (Apply → Onboard → Build → Launch → Run) is the 5-step shop window. This is the machine behind it, with the manual/hand-gloved reality flagged honestly.

Key: [K] Kade · [P] Partner · [S] System/automation. NOW = how it runs for the first partners today. NEXT = how it productises once multi-tenancy + contracts are live.

Two hard truths that shape every stage: 1. Doctrine A. Onboarding does NOT extract their method into the engine. They run BR’s doctrine, branded. Onboarding = modality + brand + scorecard + training. (Method-injection = doctrine B, later.) 2. Multi-tenancy isn’t fully built. owner_coach_id + RLS on every client-scoped table is the gate to scaling. The first one or two partners are hand-gloved (separate deploy or hand-scoped). Melisa is pilot zero — run her to harden this map before pricing the other nine.

## Stage 0 — Attract (how they find us)

Goal: the right practitioners land on the offer. - [K] Kade’s network, gym floor (Melisa), referrals, the Collective site, and later the “Powered by Body Recode” attribution on live partner sites. - Entry point: the Apply CTA on the Collective site → currently a pre-filled email to kade@bodyrecode.au. - NOW: mailto. NEXT: a proper /apply form (Tally/Typeform or native) that captures the application fields below and creates a lead record. - Exit when: an application lands.

## Stage 1 — Enquiry / Application

Goal: capture enough to qualify before spending a call. - [P] submits: name, modality, audience size + type, current tools/site, why now, what they coach. - [S]/[K] auto-response acknowledges + books a discovery call. - Assets: 04_CLIENT_LIFECYCLE/01_enquiry/ (enquiry-form, auto-response-email). - Exit when: application reviewed, call booked or politely declined.

## Stage 2 — Discovery / Qualify call (30 min)

Goal: confirm fit. Protect the standard — admitted, not signed up. - [K] runs the call against the site’s “for you / not for you” test. - Must be true: a real method, an audience that trusts them, a supported modality (strength or yoga today), ready to own not rent. - Red flags: no method (wants us to invent one), price-shopping, wants to dictate every pixel, unsupported modality with no appetite to wait. - Modality gate: if they’re Pilates/other, either waitlist them until the pack exists, or scope building that modality first (a bigger commitment). - Assets: 04_CLIENT_LIFECYCLE/02_discovery_call/. - Exit when: decision — yes / waitlist / no. If yes, move to offer.

## Stage 3 — Offer / Agreement

Goal: signed, with the model clear. - [K] presents the tier — Launch (configure existing platform) or Studio (full build) — and founding pricing (setup ~half, locked sub). - Model stated plainly: setup + monthly subscription + per active client. Powered by Body Recode. They run the engine, branded; they approve everything. - [P] signs. NOW: one-page founding-partner agreement (pilot-grade). NEXT: full IP licence + per-seat contract (currently NOT live — flagged in offer doc §7 guardrails). - [P] pays setup deposit. - Assets: 04_CLIENT_LIFECYCLE/03_quoting/, 05_LEGAL/. - Exit when: agreement signed + deposit cleared.

## Stage 4 — Onboard / Scope (the “Onboard you” step)

Goal: gather everything needed to stand up their instance. NOT method extraction. - [K]+[P] kickoff working session covering: - Modality confirmation — strength or yoga; which pack runs their brain. - Branding intake — name, colours, logo, domain, voice/tone. - Scorecard setup — BR’s scorecard logic, branded; any partner-specific copy. - Audience + first-clients plan — who their launch cohort is. - Their coaching guidance defaults — light capture (Stage 00 lite) only to set guidance-field defaults, NOT to rebuild the engine. - [K] access + accounts setup: domains, Stripe, Resend/email deliverability, 1Password vault. - Assets: 04_CLIENT_LIFECYCLE/04_onboarding/ + 00_ip_extraction/ (now light under doctrine A). - Exit when: brand assets, domain, modality, scorecard copy, and accounts are all in hand.

## Stage 5 — Build / Stand up the instance

Goal: a live, branded, working platform on their domain. - [K]/[S] provisions the instance. - NOW (hand-gloved): separate deploy or hand-scoped tenant, because multi-tenant RLS isn’t finished. Manual and careful. - NEXT: owner_coach_id provisioning — one click spins a scoped tenant. - [K] applies branding (white-label app + marketing site), configures the modality pack, stands up the branded scorecard funnel, wires payments (Stripe), email (Resend + domain), and the client portal. - [K] migrates any existing site/clients across. - Assets: 04_CLIENT_LIFECYCLE/05_build/ + 08_BUILD_PATTERNS/ (scaffold, auth, scorecard-funnel, stripe, email patterns). - Exit when: the platform passes the definition-of-done — scorecard fires a report, a client can be created, a plan can be generated and approved, payments work.

## Stage 6 — Train / Load-in

Goal: the partner can run their platform unaided. - [K] trains [P] on the ops: generating readings, approving/vetoing plans (coach-gating), logging sessions, the dashboard, the modality flow. - [P] loads in first clients (existing roster or launch cohort). - [K] hands over the credentials + how-to doc. - Assets: 04_CLIENT_LIFECYCLE/06_launch/handover-doc-template, training materials. - Exit when: partner has run the full loop once on a real client, with confidence.

## Stage 7 — Launch

Goal: the front door opens to their audience. - [P] shares the scorecard with their room; [S] segments and routes every lead. - First clients convert and onboard. - [K] on standby for launch-day issues. - Assets: 04_CLIENT_LIFECYCLE/06_launch/launch-checklist. - Exit when: scorecard is live and the first real lead/client has flowed through.

## Stage 8 — Run / Support / Grow

Goal: they run a business; we keep it healthy and expand the relationship. - [S]/[K] hosting, maintenance, support; every upgrade we ship is inherited automatically. - [S] billing: subscription monthly + per active client as the roster grows. - [K] account-health monitoring (last contact, payment, usage, stagnation). - The upsell, post-activation: once they’re live and the scorecard is filling the pipeline → offer the funnel add-on (Conversion Funnel = BR Funnel A; Challenge Funnel = BR Funnel B), re-skinned to their brand. DWY or DFY. See offer doc §4b + [[project_sot_funnel_addon_upsell]]. - Assets: 04_CLIENT_LIFECYCLE/07_run/ (ongoing-service, renewal, account-health, support-sla). - Exit when: never — this is the recurring relationship. Renewal at the annual mark.

## The honest current-state summary

| Gate | State | Blocks |
| --- | --- | --- |
| Multi-tenancy (owner_coach_id + RLS) | Not built | Scaling past 1–2 hand-gloved partners |
| IP licence + per-seat contract | Not live | Full-price selling (pilot runs on a one-pager) |
| Modality packs | strength + yoga live; Pilates next | Onboarding non-strength/yoga coaches |
| /apply form | mailto stopgap | Clean lead capture |
| Scorecard per-partner config | branded BR logic | (works; refine copy per partner) |

Sequence to de-risk: Melisa (pilot zero, contra/friendly, hand-gloved) → harden this map → build multi-tenancy + the real contract → then price and onboard the other nine off a repeatable version of this exact process.